## Sheet1
Student Name: | Kaitlyn (Ash) Moeller
Project Name | Aspen Hospital Tradegies
Game Engine: | Minecraft
Week | Asset | Description | Est. Time (Hours) | Actual Hours
| Graybox | Create the basic dimensions of each room and floor. | 2 | 6
Milestone 01 | Mobs | Implement mob spawns for each floor. NPCs stand still. Enemies move. Basement ghost only spawns if player presses admin control room button. | 1 | 2
2024-02-25 | Usable Items | Stone buttons can only be placed on white concrete. Iron pickaxe can break stone buttons and named stair. Iron sword can only kill the guard. Scarce flesh and health potions. Named paper keycards open corresponding doors. | 1 | 1
| Puzzles | Players in adventure mode. Hide chest behind wall that contains stone button and pickaxe. Hidden iron sword one hit kills guard. The guard can one hit kill the player. "Floor 1 keycard" dropped on guard death then used on hallway door. Hidden stair piece used to ascend floor 2. Hidden admin keycard opens floor 2 left side door. Admin stone button opens basement door, spawns ghost, and scream. Once in trap, ghost dies and player slowness removed. Master keycard opens door. Stone button removes blocks trapping boss. Key can be removed. Player can escape through vent or double doors. | 2 | 0.75
| Range Events | Once player is near bed, teleport player to cell. When holding correct keycard and next to door, open iron door. | 1 | 2.25
| Playtest | One at a time, let two players navigate the level. When they complete the level, ask questions and document their answers. | 2 | 0.5
| Refine | Use playtester feedback to refine the level. | 6 | 3.25
| Dynamic Visuals | As player navigates level, spawn blood, bones, and skulls. Use range events and button presses to initiate effect. | 3 | 2.5
Milestone 02 | Potion Effects | When player is in cell, give them 5 second blindness and nausea. Player has infinite slowness 2. | 1 | 0.25
2024-03-03 | Chat System | Distinguish player character thoughts, comments, and emotions using text formats. Implement during important events to indicate progress. | 1 | 2.25
| NPC Interactions | Doctor and patient dialogue. Some disappear after chat. Others question player's sanity and reality. Helpful, rude, and unstable NPCs. | 3 | 7.25
| Books | Patient mood journals and formal medical documents. | 2 | 1
| Playtest | One at a time, let two players navigate the level. When they complete the level, ask questions and document their answers. | 2 | 0.75
| Refine | Use playtester feedback to refine the level. | 3 | 1.75
| House | Spruce house. Windows. Work station has crafting table, furnance, anvil, and stone cutter. Bedroom. Decorate with unconventional methods to achieve realistic as possible detail. | 1 | 1
Milestone 03 | First Floor | Chest in all cells. Some cells have blood, bones, flesh, and skulls. Tinted windows to look through each cell. Lamps to light hallways. Hanging signs indicate room number. Mostly clean but broken. Shelves, boxes, and pillar as cover. Stairs and basement door on left side of lobby. Reception desk on right side. Blue shield with gray outline rug in middle. Double iron doors opposite of middle hallway. Windows lined around double iron doors. | 2 | 1.75
2024-03-10 | Second Floor | Long hallway to connect left and right side. Boxes to slow player movement. Locked door on each side. On left side, temporarily locked vent with ladder. Control rooms have chest, stone button, command blocks, and gray objects. Stone button key in temporarily hidden room. | 1 | 0.5
| Basement | Large cube room. Four cells on left and right side. Bloody trap in middle. Shelves and boxes allow for multiple paths. | 2 | 0.75
| Playtest | One at a time, let two players navigate the level. When they complete the level, ask questions and document their answers. | 2 | 1
| Refine | Use playtester feedback to refine the level. | 7 | 8.5
| Playtest | One at a time, let two players navigate the level. When they complete the level, ask questions and document their answers. | 2 | 1.75
Milestone 04 | Refine | Use playtester feedback to refine the level. | 13 | 14
2024-03-17
|  | Total Hours: | 60 | 60.75